## Slide 1: SITE Release 3.0 10/1/2013 – 12/31/2013
Sept 26th, 2013

## Slide 2: Agenda
SITE Goals
SITE Release 3.0
  Top Level Activities
  Resources
  Development Environment
  New Sandboxes
    PD
    QM
  Enhancements
SITE SDO Interactions
SITE Team and ESAC Team Responsibilities
Timeline and Deliverables
Risks
Next Steps

## Slide 3: SITE Goals
Enable rapid adoption of standards that support interoperability and certification
  Reduce ambiguity in standards
  Improve dialogue among implementers and SDOs
Improve implementability of standards
  Answer implementation questions clearly
  Guide issues to appropriate SDO process
  Provide test implementation on pre-ballot standards for vendors to test implementability

## Slide 4: SITE Release 3.0 – Top Level Activities
Enhancements to existing SITE Platform features
  Direct Sandbox
  C-CDA Sandbox
  Security Improvements
  SITE Usability
  SITE 508 Compliance
  Metrics and Reporting
  SDO Interactions
  Moderator Activities
New Features
  SITE development environment
  Provider Directories
  Quality Measures
  Start C-CDA R2 Incorporation

## Slide 5: SITE Release 3.0 – Resource Plan
Activity | Primary Person | SME
Direct Sandbox | Chris Cimaszewski | Nagesh Bashyam (Dragon)
Metrics and Reporting | Chris Cimaszewski | Nagesh Bashyam
Security Improvements | Chris Cimaszewski | Nagesh Bashyam
SITE Usability Improvements | Jason Goldwater | Jason Goldwater, Bill Dyer
SITE 508 Compliance/Testing | Manaar / Ai Engineer | Chris Cimaszewski
C-CDA Sandbox improvements | Dan Brown | Brett Marquard
Provider Directories | Alan Viars | Nagesh Bashyam
Quality Measures | Eric Tang | Brett Marquard
C-CDA R2 | Dan Brown, Nagesh Bashyam | Brett Marquard
SITE Development Environment | Chris Cimaszewski | Chris Cimaszewski
SDO Interactions | Bill Dyer (HL7), Nagesh Bashyam (IHE) | Brett Marquard (HL7)
SITE Moderator Activities | Bill Dyer | Bill Dyer/(Standards SMEs)
Project Management | Bill Dyer | Bill Dyer

## Slide 6: SITE - QA/Test/Dev Environment Overview
Dev-1
Apache HTTP Proxy Server
Liferay Portal
Tomcat 6, Java 6
SITE Portlets (Java Spring MVC+Bootstrap+jQuery)
3 EC2 Linux Medium Instances with the configuration shown below
SITE Dev Team
Dev-2
Direct Sandbox
  Apache James + Java RI
C-CDA R1 and R2 Validators (MDHT)
QRDA Validator (Cypress and Schematron)
  Ruby on Rails for Cypress
Tomcat 7, Java 7
MDHT Build Server using Java 5
Dev-3
SOAP Sandbox
PD Sandbox
  Apache Directory Server
  SOAP UI
  PD Build Server (Jenkins)
Tomcat 7, Java 7
SITE Development Repository: GitHub
SITE Build Tool: Maven
SITE Dev Team IDE: Eclipse

## Slide 7: SITE – New Sandboxes
Quality Measures Sandbox
QRDA Knowledge Base
QRDA Forums
QRDA Repository
QRDA Validators
QRDA Issue Tracker
Provider Directory Sandbox
PD Knowledge Base
PD Forums
PD Test Tool

## Slide 8: SITE - Provider Directory

## Slide 9: SITE - Provider Directory Scope
Integrate the PDTI tool into SITE to support developers and implementers testing the following versions of PD standards
  ModSpec v1.0
  IHE HPD with CP 601 (Not supported currently)
  EHR-IWG HPD+ 1.1
Participate in IHE WG meetings for advancing the ModSpec version within IHE
  Support technical meetings
  Support Connect-a-thons
Support Pilot participants to pilot ModSpec v1.0
  Note: EHR-IWG HPD+ 1.1 already being piloted within NYeC
Support Forum and discussion threads for ModSpec v1.1

## Slide 10: SITE - Provider Directory Sandbox Concept
Provider Directory General Information
Links to:
ModSpec Artifacts
IHE Specs
EHR – IWG Specs
PDTI Documentation
Forums
Knowledge Base
Provider Directory Test Data Download and Installation
Describe Test Data and how it can be used
Provider Directory Implementation Test Suite
Enter your PD Endpoint URL
http://myPD.com/PD
Base DN
Ou=myPD, dc=HPD
Send Query
ModSpec 1.0
IHE HPD with CP 601
EHR-IWG HPD+ 1.1
Select Test Case
Find Provider
Results Pane
Run All Conformance Tests
ModSpec 1.0
IHE HPD with CP 601
EHR-IWG HPD+ 1.1

## Slide 11: SITE - Provider Directory Sandbox Details
Test Cases Supported:
Basic Search
  Search Provider By Name
  Search Organization By Id
  Search Membership by Id
  Search Service By Id
  Search Credential by Id
Advanced Searches
  Find Individual
  Find Unique Individual
  Find Organization
  Find Unique Organization
  Find Organizations for Unique Individual
  Find Individual for Unique Organization
  Find Individuals and Organizations
  Find Service Based on Membership
Federation Test Cases
  Federation Loop Test
Other Sandbox Features
Instantiate the knowledge base within Confluence
PD Forums instantiated within SITE Forums (Dedicated Space) – Decommission Google Groups since there is no activity
  Moderated by Bill Dyer, SME - Dragon
Maintain Google Code Repository as it currently exists, export required JARS to SITE GitHub Repository for each Release.
Maintain ESAC Instance of PDTI (Since it is already paid for the next one year).

## Slide 12: SITE – Quality Measures

## Slide 13: SITE - Quality Measures Scope
Quality Measures Sandbox will be instantiated with the following capabilities:
  Links to Useful Resources (CMS, HL7, Cypress, etc.)
  Test Data Repository (Link to Cypress data)
  Issue Tracker (Link to the current CQM Issue Tracker)
    New Category will be added called “QRDA Implementation”
    CQM Issue Tracker Moderation will be performed by Julia Skapik (OCMO team) and delegate QRDA Implementation issues to SITE team
  Knowledge Base
    Only for QRDA Implementation
    Setup using Confluence as it becomes available
  Forums
    New forum setup within existing infrastructure for QRDA Implementation
    Moderated by Bill Dyer, SME – Brett Marquard

## Slide 14: SITE - Quality Measures Scope Cont’d
Quality Measures Sandbox Validators will contain the following:
  Schematron Validators
    QRDA I
    QRDA III
  Cypress Validator for Quality Measures
    Support MU Stage 2 CQM Data Set Download
    QRDA I Validator for CQM’s based on data set
    QRDA III Validator for CQM’s based on data set

## Slide 15: SITE - Quality Measures (OCMO Responsibilities)
Quality Measures OCMO and other organizations working with OCMO such as CMS, NLM, HL7 will be responsible for the following:
  CQM (Measure related questions and issues) – CMS/NQF/JC
  Value Set Issues – NLM
  QRDA I and III Standards Issues – HL7
  HQMF R1 – HL7
  Cypress – Mitre
  Cypress Test Data – Mitre
  CQM Issue Tracker Moderation – OCMO
  Delegating Implementation Issues to SITE – OCMO
  Alignment between ONC and HL7 for CQM’s - ??

## Slide 16: SITE – Quality Measure Validators
Quality Measures General Information
Links to:
HL7 Standards
Cypress
CQMs
Value Sets
Test Data
Cypress Test Data Download and installation
Describe Test Data and how it can be used
Schematron Validation Suite
Upload Your Document
C:\SampleQRDA.xml
Validate
Cypress Validation Suite
Upload Your Document
C:\SampleQRDA.xml
Validate
Choose CQM
NQF 138
Choose EH/EP
EH

## Slide 17: SITE – Enhancements

## Slide 18: SITE Usability
Feedback from the Innovation Community
  Improve Navigation
  Logos and Style Guides/templates
  Organization of Resources
  Notifications and Error Messages
  Use Bootstrap technical framework for front end
SITE Team’s Approach
  Step1: Perform usability analysis on existing SITE environment (10/4/2013)
  Step 2: Identify areas for improvement and document specific changes (10/4/2013)
  Step 3: Discuss with ONC and the Innovation Community (10/18/2013)
  Step 4: Finalize the list of changes for Release 3(10/31/2013)
  Step 5: Implement the changes for Release 3. (12/31/2013)
  Step 6: Add pending changes to Release 4

## Slide 19: SITE 508 Compliance
SITE Team’s Approach
  Step1: Perform 508 analysis by the end of the month (10/30/2013)
  Step 2: Prototype Spring MVC + Bootstrap using Progressive Enhancement for Java Script which is not supported by screen readers (10/10/2013)
  Step 3: Identify the patterns that need to be adopted by implementation team (10/10/2013)
  Step 4: Create defects for each fix required for 508 compliance
  Step 5: Assign defects to be worked as part of the Sprints.

## Slide 20: SITE Metrics and Reporting Dashboard
Forums/Issue Tracker:
Number of Forum Postings/Issues categorized by CCDA, QRDA, PD.
Number of Responses
Number of Pending Responses
Number of Open/Closed Issues
Knowledge Base:
Number of Knowledge Base web page visits organized by each knowledge base
Direct:
Number of Test Messages sent
Number of Test Messages Received
Number of Trust Anchors Uploaded
PD:
Number of Test Cases executed
CCDA:
Number of documents validated
QRDA:
Number of documents validated categorized by Schematron and Cypress

## Slide 21: SITE Direct Enhancements
Display error messages when sending messages to SUT
Display Inbox filtered by End point
Provide view access to log file
Provide Recent Activity portlet
Display error messages for trust bundle upload
Modify portlet java script to work across browsers
Modify Trust Bundle portlets to accept multiple certificate formats

## Slide 22: SITE C-CDA Enhancements
Start modeling C-CDA R2
Instantiate C-CDA base validator
Instantiate C-CDA R2 validator
Instantiate better error reporting and highlighting
Integrate GitHub Repo file repository upload and download

## Slide 23: SITE SDO Interactions
HL7
  Support discussions to align SITE and HL7 for C-CDA
IHE
  Support discussions for PD ModSpec technical discussions
  Support DAF discussions
NIST
  Discussion for eHealth Exchange validators and HealtheWay validators
  Discussion about Gazelle and future PD validators

## Slide 24: SITE Team and ESAC Team Responsibilities
ESAC
  Provide Infrastructure support for existing production SITE servers
    SITE Liferay Server
    SITE Forums Server
    SITE Apache Server
    SITE Wikispaces capability
    SITE admin mail capability
    SITE Direct + SITE Direct 2 servers
    PDTI Test Tool server
  Provide technical expertise (installation/configuration/upgrade) for
    SITE Forums
    SITE Wikispaces
    SITE Apache server
SITE Team
  Manage the content/products on Liferay, Direct, Direct2, PDTI servers
  Manage the SITE Wikispaces (Knowledge Base content) – use confluence going forward
  Manage the Forums content, accounts and moderate postings
  Manage the SITE admin mail capability
  Manage the Direct upgrades

## Slide 25: SITE Phase 3.0 Timeline
10/9
10/16
10/23
10/30
11/20
11/6
11/27
12/4
11/13
12/11
12/18
12/25
1/1
Sprint 1 Kickoff (2 week Sprints)
10/4 - Finalize Charter and Scope
Initial Usability Report
10/18 – Review with ONC and Innovation community
Finalize changes for usability
PD Sandbox Release 1
PD Sandbox Release Final
QRDA Sandbox Release 1
QRDA Sandbox Release 2
QRDA Sandbox Release 3
Metrics and Dashboard
Direct Enhancements
CCDA ERRATA completion
CCDA R2 Start
CCDA Enhancements Start
CCDA Enhancements & R2
Release 1
508 Compliance Report
Test, QA and Finalize SITE R3.0
(1/15)
R3.0 Specific 508 compliance changes

## Slide 26: Risks
508 Compliance Changes
  Need to manage the changes identified and plan to incorporate them incrementally
Usability Changes
  Need to manage the changes identified and plan to incorporate them incrementally
Quality Measure Sandbox
  Interactions between the various stakeholders and ONC SITE team has to be managed to effectively utilize and communicate Quality Measure Sandbox scope
PD Sandbox
  NIST planning to develop PD conformance tool on Gazelle.
Knowledge Base
  HL7 Knowledge Base and SITE Knowledge Base have to be designed to be complementary

## Slide 27: Testing for Phase 3
Deliverables for Phase 3 (Every Quarter) – Due 1/31/2014, need to get agreement from ONC.
  Test Plan
    High level overview of methodology
    SITE Phase 3 Instantiation diagram
    Any tools and technologies that we will be using for testing
    Bug Tracking
    Change Management
    Release Specific Testing
      High Level Capabilities that will be tested
      Outstanding bugs that need to be tested.
    Appendix
      Functional requirements or capabilities
  Test Cases
    Requirement or Capability being tested
    Preconditions
    Data Setup
      Test Steps, Results
    Post conditions and verification
  Checklist / Smoke Test to verify Production System

## Slide 28: Next Steps and Discussion
Complete Project Charter based on today’s kickoff discussion